2028 -2030 SPIL DEVELOPMENT TIMELINE

Description of the Development Timeline

The SPIL Development Committee, with the input of the Full Council, will oversee and ensure that:

- the development tasks are completed by established deadlines,

- the information gathered will result in a Plan that meets all SPIL requirements as set forth by the ACL,

- the Plan is submitted on/before the due date of June 30, 2027.

| TASK # | TASK DESCRIPTION | DATE | RESPONSIBLE PARTY* | STATUS |
| --- | --- | --- | --- | --- |
| 1 | Appoint SPIL Development Team members consisting of SILC members, ex officious, and CIL Executive Directors | January/April 2026 | Full Council | Completed at April 9th meeting. Volunteers are: Gayl, Nichole, Garrett, Lauren, and Robert. |
| 2 | SPIL Development Team meets to discuss data collection (what data can be used for Virginia trends relative to disability) and the possible need for a needs assessment. Team will develop timeline for needs assessment. | May 2026 | SPIL Development Team | 1st meeting will be May 26th |
| 3 | If a Needs Assessment is necessary, the CILs can assist with getting consumers to fill out surveys. Usually, the SILC offers a Council Approved Stipend for this work. The approved stipend for last SPIL was: Pay each CIL a minimum of $500 to conduct verifiable outreach and return of customer comment. Bonus 1: Any CIL that generates/secures 40 or more customer responses, that CIL will receive $700. Bonus 2: Any CIL that generates /secures 50 or more customer responses, that CIL will receive $900. | June-July 2026 | Full Council should approve the recommendation for any stipend to Centers |  |
| 4 | SPIL Development Team provides updates to full Council, and makes recommendations to them as needed for: - Purpose of data collection - Methods of data collection - Plans for population trend research - Preliminary budget - Preliminary Goals and Final Goals - Needs Assessment Results | # Starts July 2026; ongoing | SPIL Team |  |
| 5 | Conduct needs assessments, using recommended method(s). | July - August 2026 | SPIL Team & Staff |  |
| 6 | Sort out and analyze findings from needs assessment(s). Develop first draft of main goals | Late August - October 2026 | SPIL Team, Staff |  |
| 7 | Develop first draft of SPIL main goals based on known Needs Assessment Info. prior to October Quarterly Meeting | October 2026 | SPIL Team, Staff |  |
| 8 | Present Needs Assessment Results and Draft Goals to the Council. Council should approve the Goals with any needed modifications. | # October 2026 (even if only preliminary results) | Full Council, SPIL Team, Staff |  |
| 9 | Initiate process to allow for public commenting on proposed SPIL goals (additional survey). | # November 2026 – February 2027 | SPIL Team, Staff |  |
| 10 | Compile public comments on Goals and analyze findings. | End of February 2027 | SPIL Team, Staff |  |
| 11 | Develop a 2nd draft of goals, identify and define objectives and activities, based on public comment, if applicable. | March 2027 | SPIL Team, Staff |  |
| 12 | Develop SPIL budget with CIL Directors. | March 2027 | SPIL Team, Staff |  |
| 13 | Present final draft of goals and budget to full Council. | # April 2027 | Staff, Full Council |  |
| 14 | Create a final draft of SPIL goals, objectives and activities. | # April 2027 | SPIL Team, Staff |  |
| 15 | Notify/brief the DSE about upcoming SPIL | # March - April 2027 | Chairperson of SILC, Staff |  |
| 16 | Compile final SPIL and enter into the ACL Management Information System | May – June 2027 | Staff |  |
| 17 | Obtain signatures from the majority of the CIL Directors, the SILC Chairperson and DSE Commissioner | By June 15, 2027 | CIL Directors, Chairperson of SILC, and DSE |  |
| 18 | Submit completed SPIL to the ACL (electronically) | By June 30, 2027 | SILC Staff |  |